## SEO Checklist
Priority | Category | Task | Details | Status | Hours Spent | Notes / Result | Links
HIGH | Technical SEO | Verify Google Search Console | Make sure mahadevbooks.today is verified | Done | 0.5 | Property verified in GSC (screenshots confirmed) | https://search.google.com/search-console
HIGH | Technical SEO | Create XML sitemap | Create /sitemap.xml containing important public pages | Done | 1 | 17 URLs + lastmod dates added 8 Sep 2026 | https://mahadevbooks.today/sitemap.xml
HIGH | Technical SEO | Submit sitemap | Search Console → Sitemaps → submit sitemap.xml | Done | 0.25 | Submitted Aug 24; Status Success; 17 pages discovered
HIGH | Technical SEO | Create robots.txt | Allow public pages and reference the sitemap; exclude private/admin areas | Done | 0.5 | Allow / so Google can see noindex on login/register | https://mahadevbooks.today/robots.txt
HIGH | Technical SEO | Check indexing | Search Console → Pages; investigate excluded/not-indexed important pages | In Progress | 4 | 4 indexed / 22 not indexed. Fixed 404/403/www/index.html/WP leftovers. Awaiting Google re-crawl.
HIGH | Technical SEO | Check HTTPS | Ensure all pages use HTTPS and HTTP redirects to HTTPS | Done | 0.5 | .htaccess forces HTTPS + non-www
HIGH | Technical SEO | Canonical URLs | Add correct canonical URL to important indexable pages | Done | 1.5 | Canonicals on all indexable pages; www→apex redirect added
HIGH | On-Page SEO | Homepage title | Use one clear natural title focused on the main topic/brand | Done | 0.5 | Mahadev Book Official ¦ Cricket ID & Sports Betting Platform
HIGH | On-Page SEO | Homepage meta description | Write a unique useful description matching the actual page | Done | 0.5 | Unique description set in root layout
HIGH | On-Page SEO | One H1 per important page | Make the H1 clearly describe the page main topic | Done | 1 | Single H1 pattern used across pages
HIGH | On-Page SEO | Unique titles | Every important page should have a unique title | Done | 1.5 | Unique metadata.title per route (~19 pages)
HIGH | On-Page SEO | Unique descriptions | Write a unique meta description for each important page | Done | 1.5 | Unique metadata.description per route
MEDIUM | On-Page SEO | Heading structure | Use H2/H3 headings logically under the H1 | Done | 1 | Guides/blogs use H1→H2 structure
MEDIUM | On-Page SEO | Clean URLs | Use short descriptive URLs | Done | 0.5 | Kebab-case URLs with trailingSlash=true
MEDIUM | Images | Image filenames | Use descriptive filenames instead of image1.jpg | Partial | 0.5 | Mix of descriptive and generic/WP filenames remain
MEDIUM | Images | Alt text | Add accurate alt text where images convey useful information | Done | 1 | Descriptive alt on content images; avoid keyword stuffing
HIGH | Internal Linking | Homepage links | Link important sections from the homepage | Partial | 1 | Footer quick links expanded (incl. mahadev-book-online). Homepage body still light.
HIGH | Internal Linking | Topic clusters | Link related guides and topic pages together | Partial | 1.5 | Related links on several guides/blogs; needs stronger cluster linking
MEDIUM | Performance | Page speed | Test important pages with PageSpeed Insights | Not Started | 0 | Static export helps; PSI report not run yet | https://pagespeed.web.dev/
MEDIUM | Performance | Core Web Vitals | Check LCP INP and CLS in Search Console | Not Started | 0 | Pending GSC Experience review
HIGH | Mobile SEO | Mobile usability | Check navigation buttons text images and scrolling on phones | Partial | 1 | Responsive layout present; confirm in GSC Mobile Usability
MEDIUM | Structured Data | Organization schema | Add only if it accurately represents the organization | Done | 1 | Organization + WebSite JSON-LD on homepage
MEDIUM | Structured Data | Breadcrumb schema | Add BreadcrumbList where breadcrumbs are present | Done | 1 | BreadcrumbList via Breadcrumb component
MEDIUM | Structured Data | Article schema | Use on genuine blog/article pages | Done | 1.5 | Article schema on guides and blog posts
HIGH | Content | Create useful guides | Publish genuinely helpful content answering real user questions | Done | 12 | Cricket/IPL/UPI guides + 5 blog articles live (SEO content work)
HIGH | Content | Avoid thin/duplicate content | Do not create many pages with nearly identical text | Partial | 1 | noindex login/register; WP leftovers redirected; topical overlap still a risk
MEDIUM | Authority | Relevant mentions | Pursue legitimate relevant websites that may reference useful content | Not Started | 0 | No link-building campaign yet
HIGH | Monitoring | Weekly Search Console review | Track queries pages clicks impressions CTR and average position | In Progress | 1 | Initial deep audit done 8 Sep 2026. Set weekly cadence going forward.

## Time Summary
Metric | Value
Report date | 8 Sep 2026
Domain | mahadevbooks.today
SEO status | Technical setup mostly Done; indexing recovery In Progress; traffic still very low
Indexed pages (GSC) | 4
Not indexed pages (GSC) | 22
Clicks (last ~3 months) | 1
Impressions (last ~3 months) | 15
Sitemap | Success - 17 pages discovered
Tasks Done | 18
Tasks In Progress | 2
Tasks Partial | 5
Tasks Not Started | 3
Total SEO hours spent | 37.25
Hours for client report | 37.25 hrs (range 35-40 hrs)
Next focus | Request indexing for main URLs; weekly GSC check; CWV/speed; stronger internal links

## Hours By Category
Category | Hours | Tasks | Done
Content | 13 | 2 | 1
Technical SEO | 8.25 | 7 | 6
On-Page SEO | 6.5 | 7 | 7
Structured Data | 3.5 | 3 | 3
Internal Linking | 2.5 | 2 | 0
Images | 1.5 | 2 | 1
Mobile SEO | 1 | 1 | 0
Monitoring | 1 | 1 | 0
Performance | 0 | 2 | 0
Authority | 0 | 1 | 0